|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Name | Email | Task | Duration | Dependency | Due Date | Note |
| Alexandra Ochoa **(coordinator)** | aochoa6@student.gsu.edu | Report | 3 hrs | Lab, task 3A(questions) | 9/25 | Make sure to math the format with the one given in the prompt. |
| Aaron Anderson | aanderson124@student.gsu.edu | Programming with Nick | 5 hrs | None. | 9/30 | Finish the coding by the 22nd that way we will have time to go over it and understand it.(Task 3,B.)(the Programming task) |
| Howard King | hking10@student.gsu.edu | Questions with Mwamba | 4 hrs | None. | 10/2 | Make sure you answer all the questions with Mwamba regarding the assignment (Task 3,A.) |
| Dongmyung Lee (Nick) | dlee103@student.gsu.edu | Programming with Aaron | 5 hrs | None. | 10/2 | Work with Aaron to finish the programming part of the assignment (Task 3,B.) |
| Mwamba Chanda | mchanda1@student.gsu.edu | Questions with Howard | 4 hrs | None. | 10/2 | Work with Howard to complete the questions from (Task 3,A.) the assignment. |
| Vijayakrishna Kalavakolanu | vkalavakolanu1@student.gsu.edu | Facilitator, Scheduling, assigning roles, Maintaining Github, and help organize the report. | 2 hrs | None. | 9/25 | Upload all project documents at Github so that all team members can have access to them. And do the |